## Session 1 Oct 9
| Details | Deadline | Done | Person Responsible | Notes
PLANNING
Planning | Establish session topic(s) |  |  |  | Introduction to Open Science
| Review de-brief notes from past session | n/a | n/a | n/a
| Create online session (Microsoft Teams or Zoom) | 2020-09-30 |  | Emiko
| Create session registration page | 2020-09-30 |  | Emiko
| Prepare draft session agenda | 2020-09-30 |  | Emiko
| Prepare breakout questions |  |  | Chelsea | Confirm with Gwen
| Prepare challenges |  |  | Chelsea | Confirm with Gwen
LOGISTICS
Presenter | Identify Presenter
Invite Presenter
| Confirm Presenter |  |  |  | Gwen confirmed for session 1
| Confirm if Presenter is okay with being recorded |  |  | Chelsea
| Provide Presenter with "How to prepare a session" document |  |  | n/a | Gwen is making this document as she prepares session 1 content
Provide presenter with event information
| Create session description with Presenter |  |  | Gwen & Emiko | Make sure registration link is in session description
Facilitators | Confirm # of facilitators required |  |  |  | TBC
| Invite Lead Facilitator |  |  | Emiko | Emiko lead for first session
| Invite Chat Facilitator |  |  | Chelsea | Chelsea chat for first session
| Invite Breakout Facilitators | 2020-10-02 |  |  | TBC
| Provide lead facilitator with land acknowledgement script and agenda |  |  | Emiko
| Provide all facilitators with breakout questions, challenges, and "How to faciliate" guidelines |  |  | Emiko
| Provide co-host priviledges to all facilitators in advance of session |  |  | Emiko
Debrief/ Wrap-up | Add debrief to next organizer meeting agenda |  |  |  | TBC
| Prepare notes on how the session went for debrief | 2020-10-09 |  | Emiko & Chelsea
| Send thank you email to Presenter & Facilitators |  |  |  | TBC
COMMUNICATIONS
Promotion | Provide session description to Promotions team |  |  | Gwen & Emiko | Make sure registration link is in session description