## Session 1 Oct 9
| Details | Ideal timeline (done) | Deadline | Person Responsible | Status (in progress/done) | Notes
2-4 WEEKS PRE-EVENT
| Find co-organizers (if any) | ~3 weeks pre-event
| Establish event topic | ~3 weeks pre-event
| Pick a date and time for your event - sign your group up in the Event Planning document: https://docs.google.com/document/d/1lVpZ3pljEu9A6WsqLUFKDL--yv3yvycRhqrCxfswgdo/edit?usp=sharing | ~2-3 weeks pre-event |  |  |  | An event coordinator will be in touch after you sign up - you can also get in touch with them yourselves
| Decide on the main components/format of your event (e.g. presentation, discussion, workshop, social, hackathon) - you can combine more than one into a single event (this is usually good for engagement) | ~2-3 weeks pre-event
| Identify potential presentors/workshop leads - anyone you'd like to deliver content during your event | ~2-3 weeks pre-event
| Write event description for promotional purposes (~1 short paragraph) | ~2-3 weeks pre-event
| Create Zoom meeting and registration page | ~2-3 weeks pre-event
| Invite potential presenters/workshop leads/anyone you'd like to deliver content | ~2.5 weeks pre-event
| Send promotional blurb and zoom registration information to promotions unit for dissemmination | 2 weeks pre-event
| Start preparing more content-heavy event materials (e.g. workshop materials, presentations) | ~2 weeks pre-event
1-2 WEEKS PRE-EVENT
| Confirm presenters/workshop leads/anyone you'd like to deliver content | 1.5 weeks pre-event
| Identify potential facilitator(s) - anyone you'd like to be involved in leading the event. You will need a main facilitator for all events, and a chat/zoom facilitator for online events. If you are planning discussions in small groups (e.g. 3-5 people), you can also consider inviting facilitators for these small group discussions | ~1-2 weeks pre-event
| Prepare lighter event materials (this includes check-in prompts, discussion questions, exercises, etc.) | ~1-2 weeks pre-event
| Invite potential main and chat/zoom facilitators | 1 week pre-event
| Prepare land acknowledgement | 1 week pre-event
| Work on heavier event materials (e.g. workshop materials, presentations) | 1 week pre-event
| Decide on smaller components of your event (e.g. check-in round, closing activity, etc.) | 1 week pre-event
WEEK OF EVENT
| Prepare draft of event agenda (detailed overview of activities & timing, see template: https://osf.io/sm9bd/) | ~6 days pre-event
| Confirm Main & Chat/zoom facilitators | ~4 days pre-event
| Invite Breakout Facilitators (if applicable) | ~4 days pre-event
| Invite Main Facilitator to personalize land acknowledgement | ~4 days pre-event
| Personalize feedback survey - see template: | ~3 days pre-event
| Finalize event materials | ~2 days pre-event
| Finalize event agenda | ~2 days pre-event
1 DAY PRE-EVENT
| Check number of participants registered and confirm # of Breakout Facilitators required | 1 day pre-event
| Confirm Breakout Facilitators | 1 day pre-event
| Provide facilitators with event information (e.g. share event agenda) | 1 day pre-event
DAY OF EVENT
| Send reminder email to registered participants | ~1-2 hour pre-event
| Sign into Zoom & provide co-host privileges to all facilitators in advance of session | ~15 min pre-event
POST EVENT
| Send thank you email to Presenter & Facilitators | ~1-4 days post-event
| Upload shareable event materials to OSF and post materials and feedback survey link on Slack | ~1-4 days post-event
| Look at feedback survey responses | ~3-7 days post-event
| Prepare notes on how the even went for debrief | ~1-7 days post-event
Join next general meeting to debrief event